## 📊 Project Overview
LINGUALLEARN AI - PROJECT TRACKER
Project Name: | LinguaLearn AI
Project Type: | MLOps Engineer Portfolio
Duration: | 8 Weeks (90-120 hours total)
Start Date: | Week 1 Complete
Current Phase: | Phase 5 - Monitoring & Security
Overall Status: | Blcoked
Tech Stack: | AWS (VPC, EC2, RDS, Lambda, S3, CloudFront, ALB, CloudWatch, Secrets Manager), Terraform, Python, FastAPI, PostgreSQL
PHASE SUMMARY
Phase | Description | Status | Start Date | Target End | Completion % | Blocker Count | Notes
1 | Infrastructure Foundation | Complete | Week 1 Day 1 | Week 1 Day 5 | 100% | 0 | VPC, RDS, Security Groups deployed
2 | API & Compute Layer | Complete | Week 2 Day 1 | Week 2 Day 5 | 100% | 0 | SSM connectivity issue, Git sync issue
3 | Multi-Modal Tracking & Video | Complete | Week 3 Day 1 | Week 3 Day 5 | 100% | 0 | Later Enhancement items
4 | ML Integration & AnkiDeck API | Complete | Week 4 Day 1 | Week 4 Day 5 | 100% | 0 | Lambda size limit - optimization
5 | Monitoring & Security | In progress | Week 5 Day 1 | Week 5 Day 5 | 0% | 0
6 | CI/CD & Demo | Not Started | Week 6 Day 1 | Week 6 Day 5 | 0% | 0
KEY METRICS
Total Tasks: | 152
Completed: | 80 (58%)
In Progress: | 1 (1%)
Blocked: | 0 (0%)
Not Started: | 53 (40%)
Current Week Hours: | 8 / 15
Total Hours Logged: | 91.5 / 120
Estimated Completion: | Week 6 Day 5

## Phase 1 - Infrastructure
PHASE 1: Infrastructure Foundation
Status: | Complete
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P1-T001 | Day 1 | AWS Account Setup & Billing Alarms | AC | Complete | High | 0.5 | 0.5
P1-T002 | Day 1 | Create IAM Admin User with MFA | AC | Complete | High | 0.5 | 0.5
P1-T003 | Day 1 | Install AWS CLI & Terraform | AC | Complete | High | 0.5 | 0.5
P1-T004 | Day 1 | Initialize Terraform Project Structure | AC | Complete | High | 1 | 1
P1-T005 | Day 2 | Create VPC with Public/Private Subnets | AC | Complete | High | 2 | 2.5 |  | Multi-AZ setup
P1-T006 | Day 2 | Deploy NAT Gateway & Internet Gateway | AC | Complete | High | 1 | 1
P1-T007 | Day 2 | Configure Route Tables | AC | Complete | High | 0.5 | 0.5
P1-T008 | Day 3 | Create Security Groups (ALB, EC2, RDS, Lambda) | AC | Complete | High | 2 | 2 |  | Zero-trust model
P1-T009 | Day 4 | Create RDS PostgreSQL (Multi-AZ) | AC | Complete | High | 1.5 | 2
P1-T010 | Day 4 | Configure Secrets Manager | AC | Complete | High | 0.5 | 0.5
P1-T011 | Day 5 | Set up CloudWatch Log Groups | AC | Complete | Medium | 1 | 1
P1-T012 | Day 5 | Configure VPC Flow Logs | AC | Complete | Medium | 0.5 | 0.5
P1-T013 | Day 5 | Documentation & Testing | AC | Complete | High | 2 | 2
P1-T014 | Day 5 | LinkedIn Post - Week 1 | AC | Complete | Low | 0.5 | 0.5

## Phase 2 - API & Compute
PHASE 2: API & Compute Layer
Status: | Complete
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P2-T001 | Day 1 | Create EC2 Instance in Terraform | AC | Complete | High | 1 | 1
P2-T002 | Day 1 | Create IAM Role for EC2 | AC | Complete | High | 0.5 | 0.5
P2-T003 | Day 1 | Create user_data.sh Script | AC | Complete | High | 0.5 | 0.5
P2-T004 | Day 1 | Deploy EC2 and Configure SSM | AC | Complete | High | 1 | 2 | SSM Agent not connecting | Need VPC endpoints + SSM Agent
P2-T005 | Day 2 | Create Database Schema (12+ tables) | AC | Complete | High | 1.5 | 2 | Git sync issue | Remove nested repo
P2-T006 | Day 2 | Set Up API Project Structure | AC | Complete | High | 1 | 0.5
P2-T007 | Day 2 | Build Database Connection Utility | AC | Complete | High | 1 | 0.5
P2-T008 | Day 2 | Create FastAPI Main Application | AC | Complete | High | 1 | 1
P2-T009 | Day 2 | Build Health Check Endpoint | AC | Complete | High | 0.5 | 0.5
P2-T010 | Day 3 | Create User Management Endpoints | AC | Complete | High | 2 | 2
P2-T011 | Day 3 | Create Vocabulary CRUD Endpoints | AC | Complete | High | 2 | 2
P2-T012 | Day 3 | Test Endpoints | AC | Complete | High | 1 | 1
P2-T013 | Day 4 | Create Application Load Balancer | AC | Complete | High | 1.5 | 1
P2-T014 | Day 4 | Configure SSL Certificate | AC | Complete | High | 1 | 1.5
P2-T015 | Day 4 | Set Up Target Groups | AC | Complete | High | 1 | 0.5
P2-T016 | Day 4 | Configure systemd Service | AC | Complete | Medium | 0.5 | 0.5
P2-T017 | Day 5 | API Testing | AC | Complete | High | 1.5 | 1.5
P2-T018 | Day 5 | Configure CloudWatch Logs | AC | Complete | Medium | 1 | 1
P2-T019 | Day 5 | API Documentation | AC | Complete | High | 1.5 | 0.5
P2-T020 | Day 5 | Phase 2 Complete Docs | AC | Complete | High | 1 | 0.5
P2-T021 | Day 5 | LinkedIn Post - Week 2 | AC | Complete | Low | 0.5 | 0.5

## Phase 3 - Multi-Modal
PHASE 3: Multi-Modal Tracking & Video
Status: | Complete
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P3-T001 | Day 1 | Create S3 Data Lake Bucket | AC | Complete | High | 1 | 1
P3-T002 | Day 1 | Create S3 Video Storage Bucket | AC | Complete | High | 0.5 | 0.5
P3-T003 | Day 1 | Configure S3 Bucket Policies | AC | Complete | High | 1 | 1
P3-T004 | Day 1 | Create CloudFront Distribution | AC | Complete | High | 1.5 | 1.5
P3-T005 | Day 1 | Upload Sample ASL Videos (10-20) | AC | Complete | Medium | 1 | 2
P3-T006 | Day 2 | Create Practice Activity Routes | AC | Complete | High | 2 | 2
P3-T007 | Day 2 | Build Language Assignment Endpoints | AC | Complete | High | 1.5 | 0 |  | Later enhancement
P3-T008 | Day 2 | Update Main FastAPI App | AC | Complete | High | 0.5 | 0.5
P3-T009 | Day 2 | Test Practice Endpoints | AC | Complete | High | 1 | 1
P3-T010 | Day 3 | Create Lambda Handler for Video Metadata | AC | Complete | High | 2 | 2
P3-T011 | Day 3 | Create Lambda Infrastructure in Terraform | AC | Complete | High | 1.5 | 1.5
P3-T012 | Day 3 | Package and Deploy Lambda Function | AC | Complete | High | 1 | 1
P3-T013 | Day 3 | Test Lambda with S3 Upload | AC | Complete | High | 1 | 0.5
P3-T014 | Day 3 | Verify S3 Event Triggers | AC | Complete | Medium | 0.5 | 0.5
P3-T015 | Day 3 | Create ASL Vocabulary Endpoints | AC | Complete | High | 2 | 2.5 | Authentication error | Reset Secret
P3-T016 | Day 3 | Populate asl_vocabulary Table | AC | Complete | High | 1 | 1
P3-T017 | Day 3 | Test Video Streaming | AC | Complete | High | 1 | 1
P3-T018 | Day 4 | Create Data Generation Script | AC | Complete | High | 2 | 0 |  | Future Demos
P3-T019 | Day 4 | Generate 100 Synthetic Users | AC | Complete | Medium | 1 | 0 |  | Furture Demos
P3-T020 | Day 4 | Generate 500+ Practice Activities | AC | Complete | Medium | 1.5 | 0 |  | Furture Demos
P3-T021 | Day 5 | Load Test Video Streaming | AC | Complete | Medium | 1 | 1
P3-T022 | Day 5 | Verify CloudFront Cache Hit Rates | AC | Complete | Medium | 0.5 | 0.5
P3-T023 | Day 5 | Update Architecture Diagram | AC | Complete | High | 1 | 0
P3-T024 | Day 5 | Phase 3 Documentation | AC | Complete | High | 1.5 | 1
P3-T025 | Day 5 | LinkedIn Post - Week 3 | AC | Complete | Low | 0.5 | 0.5

## Phase 4 - ML Integration
PHASE 4: ML Integration & AnkiDeck API
Status: | Complete
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P4-T001 | Day 1 | Create Forgetting Curve Model | AC | Complete | High | 2 | 2
P4-T002 | Day 1 | Train Model on Synthetic Data | AC | Complete | High | 1.5 | 1.5
P4-T003 | Day 1 | Save Model as .pkl File | AC | Complete | High | 0.5 | 0.5
P4-T004 | Day 1 | Upload Model to S3 | AC | Complete | High | 0.5 | 0.5
P4-T005 | Day 2 | Create Lambda Handler for ML Inference | AC | Complete | High | 2 | 2
P4-T006 | Day 2 | Create Lambda in Terraform | AC | Complete | High | 1.5 | 1.5
P4-T007 | Day 2 | Configure Lambda IAM Permissions | AC | Complete | High | 0.5 | 0.5
P4-T008 | Day 2 | Test Lambda Directly | AC | Complete | High | 1 | 4 | AWS Resource size limit | Lambda Layers to separate dependencies
P4-T009 | Day 3 | Create Prediction API Endpoint | AC | Complete | High | 2 | 2
P4-T010 | Day 3 | Store Predictions in RDS | AC | Complete | High | 1 | 1
P4-T011 | Day 3 | Test Prediction Endpoint | AC | Complete | High | 1 | 2 |  | Resolved a few errors
P4-T012 | Day 4 | Research AnkiDeck API | AC | Complete | Medium | 1 | 2 | No AnkiDeck integration | Manual Curated vocabulary
P4-T013 | Day 4 | Create Vocubulary Seed Files | AC | Complete | High | 2 | 3
P4-T014 | Day 4 | Create Vocabulary Seeding Script | AC | Complete | High | 1.5 | 1.5
P4-T015 | Day 4 | Seed Vocabulary Database & Verify Data Integrity | AC | Complete | High | 1 | 2.5 | UTF-8 encoding challenges
P4-T016 | Day 5 | Create EventBridge Rules | AC | Complete | High | 1.5 | 0 |  | Cancelled - pivot from AnkiDeck API
P4-T017 | Day 5 | Test Scheduled Jobs | AC | Complete | High | 1 | 0 |  | Cancelled - pivot from AnkiDeck API
P4-T018 | Day 5 | Implement Model Versioning | AC | Complete | Medium | 1 | 1
P4-T019 | Day 5 | Phase 4 Documentation | AC | Complete | High | 1.5 | 1.5
P4-T020 | Day 5 | LinkedIn Post - Week 4 | AC | Complete | Low | 0.5 | 0.5

## Phase 5 - Monitoring
PHASE 5: Monitoring & Security
Status: | In progress
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P5-T001 | Day 1 | Apply DB Connection Context Manager | AC | In Progress | High | 1 | 0 |  | See docs/code-quality/CONNECTION_POOL_MANAGEMENT.md
P5-T002 | Day 1 | Implement Structured Error Handling | AC | Not Started | High | 1.5 | 0 |  | See docs/code-quality/ERROR_HANDLING_PATTERNS.md
P5-T003 | Day 1 | Fix ML Model (LogisticRegression, train/test split, quality gate) | AC | Not Started | High | 2 | 0 |  | See docs/code-quality/ML_MODEL_EVALUATION.md
P5-T004 | Day 1 | Apply Terraform Security Fixes | AC | Not Started | High | 1 | 0 |  | See docs/code-quality/INFRASTRUCTURE_SECURITY_HARDENING.md
P5-T005 | Day 1 | Verify Security Group Rules | AC | Not Started | Medium | 0.25 | 0 |  | Consolidated — verify SSH removed, ALB-only ingress
P5-T006 | Day 1 | Check IAM Policies | AC | Not Started | Medium | 0.25 | 0 |  | Consolidated — verify scoped Secrets Manager, separate Lambda roles
P5-T007 | Day 1 | Verify Encryption (Rest & Transit) | AC | Not Started | Medium | 0.25 | 0 |  | S3 encryption, RDS encryption, HTTPS on ALB
P5-T008 | Day 2 | Create CloudWatch Dashboard | AC | Not Started | High | 2 | 0 |  | 6 widgets: API latency, error rates, Lambda duration, RDS connections, S3 requests, ALB metrics
P5-T009 | Day 2 | Configure CloudWatch Alarms | AC | Not Started | High | 1 | 0 |  | 4 alarms: High error rate, Lambda throttling, RDS connection spike, API latency
P5-T010 | Day 2 | Set Up SNS Topic for Alerts | AC | Not Started | High | 0.5 | 0 |  | Email notifications for alarm triggers
P5-T011 | Day 2 | Enable VPC Flow Logs | AC | Not Started | Medium | 0.25 | 0 |  | CloudWatch log group with 30-day retention
P5-T012 | Day 2 | Test Alarm Triggers | AC | Not Started | Medium | 1 | 0
P5-T013 | Day 2 | Create Operational Runbook | AC | Not Started | Medium | 3 | 0
P5-T014 | Day 3 | Create Multi-Stage Dockerfile | AC | Not Started | High | 2 | 0 |  | Target image size <300MB, separate build/runtime stages
P5-T015 | Day 3 | Create docker-compose.yml | AC | Not Started | Medium | 0.5 | 0
P5-T016 | Day 3 | Test Local Container Build | AC | Not Started | High | 0.5 | 0 |  | docker build + docker run + health check
P5-T017 | Day 3 | Create ECR Repository | AC | Not Started | Medium | 0.5 | 0
P5-T018 | Day 3 | Push Image to ECR | AC | Not Started | Medium | 1 | 0
P5-T019 | Day 3 | Document Docker Workflow | AC | Not Started | Low | 1 | 0 |  | docs/DOCKER.md — build, run, push commands
P5-T020 | Day 4 | Install Mlflow | AC | Not Started | High | 1 | 0
P5-T021 | Day 4 | Update Training Script with MLflow Tracking | AC | Not Started | High | 1.5 | 0 |  | Log params, metrics, artifacts for each run
P5-T022 | Day 4 | Run 5 Experiment Variations | AC | Not Started | Medium | 1 | 0 |  | Vary hyperparameters, compare in MLflow UI
P5-T023 | Day 4 | Register Best Model | AC | Not Started | Medium | 0.5 | 0 |  | Promote to MLflow Model Registry
P5-T024 | Day 4 | Document MLflow Setup | AC | Not Started | Low | 0.5 | 0 |  | docs/MLFLOW_SETUP.md — setup, usage, comparison
P5-T025 | Day 4 | Install Load Testing Tools | AC | Not Started | Medium | 0.25 | 0 |  | Locust
P5-T026 | Day 4 | Create Load Testing Scripts | AC | Not Started | Medium | 1
P5-T027 | Day 4 | Run Load Tests (100 users) | AC | Not Started | Medium | 0.5 | 0 |  | 5-minute test, capture latency/throughput
P5-T028 | Day 4 | Test Video Streaming Under Load | AC | Not Started | Low | 0.5 | 0
P5-T029 | Day 5 | Implement API Rate Limiting | AC | Not Started | High | 1 | 0 |  | slowapi with tiered limits (100/min general, 20/min predictions)
P5-T030 | Day 5 | Add Custom ML CloudWatch Metrics | AC | Not Started | Medium | 1 | 0 |  | Prediction latency, model version, recall probability distribution
P5-T031 | Day 5 | Update README with Phase 5 Changes | AC | Not Started | Medium | 0.5 | 0 |  | Monitoring, Docker, MLflow sections
P5-T032 | Day 5 | Create MONITORING.md | AC | Not Started | Low | 1 | 0 |  | Dashboard overview, alarm thresholds, runbook reference
P5-T033 | Day 5 | Final Phase 5 Verification | AC | Not Started | High | 1.5 | 0 |  | End-to-end test: API → Lambda → CloudWatch → Alarm
P5-T034 | Day 5 | LinkedIn Post - Week 5 | AC | Not Started | Low | 0.5 | 0

## Phase 6 - CICD
PHASE 6: CI-CD & Demo
Status: | Not Started
Task ID | Day | Task Description | Owner | Status | Priority | Est Hours | Actual Hours | Blocker | Notes
P6-T001 | Day 1 | Create GitHub Actions Workflow | AC | Not Started | High | 2 | 0
P6-T002 | Day 1 | Configure Terraform Deploy Pipeline | AC | Not Started | High | 1.5 | 0
P6-T003 | Day 1 | Configure AWS Credentials in GitHub | AC | Not Started | High | 0.5 | 0
P6-T004 | Day 1 | Test CI/CD Pipeline | AC | Not Started | High | 1 | 0
P6-T005 | Day 2 | Create Architecture Diagram | AC | Not Started | High | 2 | 0
P6-T006 | Day 2 | Update Complete README | AC | Not Started | High | 2 | 0
P6-T007 | Day 2 | Polish All Documentation | AC | Not Started | High | 1.5 | 0
P6-T008 | Day 3 | Plan Demo Video Script | AC | Not Started | High | 1 | 0
P6-T009 | Day 3 | Record Demo Video (3-5 min) | AC | Not Started | High | 2 | 0
P6-T010 | Day 3 | Edit and Add Captions | AC | Not Started | Medium | 1 | 0
P6-T011 | Day 3 | Upload to YouTube | AC | Not Started | Low | 0.5 | 0
P6-T012 | Day 4 | Clean Up Terraform Code | AC | Not Started | Medium | 1.5 | 0
P6-T013 | Day 4 | Refactor API Code | AC | Not Started | Medium | 1.5 | 0
P6-T014 | Day 4 | Final Cost Optimization Review | AC | Not Started | Medium | 1 | 0
P6-T015 | Day 4 | Document AWS to Azure Migration | AC | Not Started | Low | 1 | 0
P6-T016 | Day 5 | Prepare Interview Talking Points | AC | Not Started | High | 2 | 0
P6-T017 | Day 5 | Update Portfolio Site | AC | Not Started | High | 1.5 | 0
P6-T018 | Day 5 | Create Lessons Learned Doc | AC | Not Started | High | 1 | 0
P6-T019 | Day 5 | Final Git Commit | AC | Not Started | High | 0.5 | 0
P6-T020 | Day 5 | LinkedIn Post - Project Complete! | AC | Not Started | High | 1 | 0

## ⚠️ Blockers & Risks
BLOCKERS & RISKS LOG
ID | Phase | Task ID | Description | Impact | Status | Owner | Action Plan | Resolution Date
B001 | Phase 2 | P2-T004 | SSM Agent cannot connect to EC2 | High | Resolved | AC | 1. Verify VPC endpoints created 2. Check IAM instance profile 3. Verify SSM Agent installed in user_data.sh 4. Check security groups 5. Recreate EC2 if needed | 2025-11-13
B002 | Phase 2 | P2-T005 | Git repository sync - nested repo conflict | High | Resolved | AC | 1. Backed up terraform files 2. Removed nested .git 3. Moved terraform to root 4. Resolved merge conflicts 5. Force pushed | 2025-11-14
B003 | Phase 4 | P4-T015 | UTC-8 Encoding | Medium | Resolved | AC | 1. Upload files to S3 2. SSM into EC2 3. Dowload files | 2025-12-26
B004 | Phase 5 | P5-T001 | Security review identified connection pooling that needs remediation | High | In progress | AC | See docs/code-quality/CONNECTION_POOL_MANAGEMENT.md
B005 | Phase 5 | P5-T002 | Security review identified error handling that needs remediation | High | Not Started | AC | See docs/code-quality/ERROR_HANDLING_PATTERNS.md
B006 | Phase 5 | P5-T003 | Security review identified ML evaluation patterns that needs remediation | High | Not Started | AC | See docs/code-quality/ML_MODEL_EVALUATION.md
B007 | Phase 5 | P5-T004 | Security review identified permission issues that need remediation | High | Not Started | AC | See docs/code-quality/INFRASTRUCTURE_SECURITY_HARDENING.md
B008 | Phase 5 | P5-T005 | Security review identified permission issues that need remediation | High | Not Started | AC | See docs/code-quality/INFRASTRUCTURE_SECURITY_HARDENING.md
B009 | Phase 5 | P5-T006 | Security review identified permission issues that need remediation | High | Not Started | AC | See docs/code-quality/INFRASTRUCTURE_SECURITY_HARDENING.md
B010 | Phase 5 | P5-T007 | Security review identified permission issues that need remediation | High | Not Started | AC | See docs/code-quality/INFRASTRUCTURE_SECURITY_HARDENING.md

## 📝 Change Log
PROJECT CHANGE LOG
Date | Changed By | Phase/Task | Change Type | Description | Impact
2025-11-06 | AC | Phase 1 | Phase Complete | Infrastructure Foundation complete - 100% | Low
2025-11-13 | AC | Phase 2 | Blocker Added | SSM connectivity issue - requires VPC endpoints + SSM Agent installation | High
2025-11-14 | AC | Phase 2 | Blocker Added | Git sync issue- nested repo + restructured folders | High
2025-11-26 | AC | Phase 2 | Phase Complete | API & compute layer complete - 100% | High
2025-12-07 | AC | Phase 3 | Phase Complete | Multi-Modal Activity Tracking complete - 97% | Medium
2025-12-15 | AC | Phase 4 | Task Set | AnkiDeck API Integration to Seeded Vocabulary | Medium
2025-12-30 | AC | Phase 4 | Phase Complete | ML Integration - 100% | High
2026-03-26 | AC | Phase 5 | Scope Addition | Added "Code Quality & Security Hardening" day based on collaborative security review. Includes: context manager for DB connections, structured error handling, ML model fixes (LogisticRegression, train/test split, quality gate), Terraform security (scoped IAM, separated Lambda roles, S3 blocks, SSH removal) | High
2026-03-26 | AC | Phase 5 | Schedule Update | Day 1 now covers code quality fixes (6.25 hrs); total Phase 5 timeline adjusted to ~23 hours | High
2026-03-26 | AC | Phase 6 | Scope Reduction | "Refactor API code" task reduced to formatting/linting only; substantive refactoring moved to Phase 5 Day 1 | Medium
2026-03-26 | AC | Documentation | Addition | Added SECURITY_CONSIDERATIONS.md documenting auth approach as known limitation with solutions | Low
2026-03-26 | AC | Documentation | Addition | Added docs/code-quality folder with lessons learned: CONNECTION_POOL_MANAGEMENT.md, ERROR_HANDLING_PATTERNS.md, ML_MODEL_EVALUATION.md, INFRASTRUCTURE_SECURITY_HARDENING. | Low

## 📖 How to Use
PROJECT TRACKER - USAGE INSTRUCTIONS
DAILY WORKFLOW
1. Update Task Status | Change status dropdown: Not Started → In Progress → Complete
2. Log Hours | Update 'Actual Hours' column as you work
3. Add Blockers | Document any blockers in 'Blocker' column
4. Add Notes | Capture learnings in 'Notes' column
WEEKLY WORKFLOW
1. Review Overview Tab | Check phase completion % and metrics
2. Update Blockers Sheet | Add new blockers, update status on existing
3. Add Change Log Entry | Document major changes or decisions
4. LinkedIn Update | Post weekly progress (use template in task)
AUTOMATION TIPS
Status Dropdowns | Click cells in Status column for dropdown
Priority Highlighting | High priority tasks are bold red
Color Coding | Green=Complete, Yellow=In Progress, Red=Blocked, Gray=Not Started
Filtering | Use Excel filters on header row to view specific statuses
GITHUB INTEGRATION
Link to GitHub | Use Task IDs in commit messages: 'git commit -m "Fix #P2-T004"'
Create GitHub Issues | Copy tasks to GitHub Projects for daily tracking
Sync Weekly | Update this tracker from GitHub once per week
INTERVIEW PREP
Completed Tasks | Use to talk about specific accomplishments
Blockers Resolved | Great stories for problem-solving questions
Hours Logged | Shows time management skills
Phase Completion | Demonstrates ability to deliver projects